Sprint 01 — Foundations Week

Dates: Monday, May 25, 2026 → Friday, May 29, 2026

Increment: Inc 1 — Foundations & Finish Core Loop

Team: Emma, Nikki, Jaliah

Sprint goal: Lay the infrastructure that lets us move fast — OpenAPI spec, CI, observability, canonical API URL — and start the marketing track.

Demo target (Friday, May 29)

By the end of Friday's review meeting, we should be able to show:

•	
      ☐ Swagger UI reachable from a URL — showing /auth/*, /trips/*, and /ai/itinerary/generate schemas

•	
      ☐ GitHub Actions CI green on a sample PR (lint + spec validate + integration tests)

•	
      ☐ Mobile app talking to the canonical API Gateway URL — no more URL drift between docs and code

•	
      ☐ Sentry catching a deliberately thrown error from both backend and mobile

•	
      ☐ Positioning doc shared with team; social handles and domain reserved

Task assignments

Emma

•	
      A1 — Resolve API Gateway URL mismatch. Pick the canonical URL between 1w6itm4sqj.execute-api… (backend docs) and gaq4nwm4l6.execute-api… (mobile api.ts). Update TripApp_AIChallange/mobile/src/services/api.ts and the various *.md docs at repo root. Open a single PR.

•	
      A2 — Set up Sentry on backend Lambdas via serverless-sentry-lib or sentry-sdk[serverless]. Add SENTRY_DSN to env vars. Throw a test error and verify it appears in Sentry.

•	
      A3 — Set up Sentry on mobile via @sentry/react-native (Expo-compatible build). Wrap App in a Sentry boundary. Trigger a deliberate error and verify.

•	
      Run Sprint 1 planning meeting Monday 9:00 AM. Walk Nikki and Jaliah through this document. Confirm the Slack or Discord channel for standups.

•	
      Marketing — Buy the domain (chronicle.travel or chosen alt). Reserve handles on Instagram, TikTok, X, Threads, YouTube. Draft a one-page positioning doc: one-sentence value prop + 3 differentiators + target persona.

Nikki

•	
      A4 — Hand-write backend/openapi.yaml (OpenAPI 3.1) covering all 4 auth endpoints: POST /auth/signup, /auth/login, /auth/confirm, and /auth/resend. Include request/response/error schemas with examples. Reference backend/handlers/auth.py for actual behavior.

•	
      A6 — Stand up Swagger UI. Easiest path: serve the Swagger UI HTML from a Lambda or a static S3 bucket, pointing it at the openapi.yaml hosted in the same bucket. Internal-only (basic auth or behind VPN — discuss with Emma).

•	
      Pair with Jaliah Tuesday afternoon on CI scaffolding — agree on the spec validation tool (@redocly/cli or swagger-cli).

Jaliah

•	
      A5 — Hand-write backend/openapi.yaml entries for POST /trips, GET /trips, GET/PUT/DELETE /trips/{trip_id}, and POST /ai/itinerary/generate. Coordinate with Nikki to keep the file format consistent.

•	
      A7 — Set up GitHub Actions CI in .github/workflows/ci.yml:

◦	
      Trigger on PR to main

◦	
      Job 1: install Python deps, run flake8 or ruff on backend/ + ai-layer/

◦	
      Job 2: validate backend/openapi.yaml with the tool Nikki picks

◦	
      Job 3: run backend/tests/integration_test.py against a test Cognito user (repo secrets for TEST_EMAIL, TEST_PASSWORD, API_URL)

•	
      A8 — Write infrastructure/DEPLOY.md documenting serverless deploy --stage dev vs --stage staging (staging stage to be created in Sprints 2-3) and the env vars each requires.

Dependencies & sequencing

•	
      Nikki's A4 (auth spec format) should land Monday or Tuesday so Jaliah's A5 (trips spec) can match the same conventions.

•	
      Jaliah's A7 (CI) depends on having an OpenAPI file to validate — so it waits until at least A4 is in the repo (target: Tuesday EOD).

•	
      Emma's A1 (URL fix) can happen any time but the mobile rebuild for Friday's demo depends on it being merged by Thursday.

•	
      A2 + A3 (Sentry) are independent — Emma can do them in parallel with the other work.

Critical path: A4 → A5 / A7 → demo.

Daily standup tracker

Post 3-line update in #chronicle-standup by 10:00 AM. Yesterday / Today / Blockers.

Day

Emma

Nikki

Jaliah

Mon May 25

Tue May 26

Wed May 27

Thu May 28

Fri May 29

Notes for the planning meeting (Mon 9:00 AM)

1	
      Confirm everyone has access to: GitHub repo, AWS console (read-only OK), Sentry organization (Emma creates), Slack or Discord.

2	
      Confirm working hours and timezone overlap.

3	
      Confirm reviewer pairings (defaults in TEAM.md).

4	
      Open questions from MARKETING.md — get the team's input on target persona and monetization.

5	
      Walk through PROCESS.md Definition of Done — agree on it before Sprint 1 work starts.

Sprint review (fill in Friday afternoon)

Task

Owner

Status

Notes

A1 — API URL reconcile

Emma

A2 — Backend Sentry

Emma

A3 — Mobile Sentry

Emma

Marketing — domain + handles + positioning

Emma

A4 — Auth OpenAPI

Nikki

A6 — Swagger UI

Nikki

A5 — Trips + AI OpenAPI

Jaliah

A7 — CI pipeline

Jaliah

A8 — Deploy doc

Jaliah

Shipped:

•

Carryover to next sprint:

•

Dropped (with reason):

•

Retro notes (Friday — first retro of the project)

Keep

•

Change

•

Try (next 2 weeks)

•

Action items

•	
      ☐ who · what · by when